## Sheet1
Project / System Category | Risks | Severity | Priority | Mitigation Strategy
System | System Scalability Issues | 3 | 2 | Utilize cloud-based solutions and load balancing to ensure system scalability.
System | Integration Complexity | 3 | 3 | Conduct phased integration with existing Delta systems and perform rigorous API testing.
System | Data Accuracy & Consistency | 3 | 2 | Implement strong data validation protocols and real-time synchronization mechanisms.
Project | User Adoption Challenges | 2 | 3 | Provide extensive training and support for internal teams and customers.
System | Insufficient Testing Before Deployment | 3 | 2 | Implement rigorous testing strategies, including unit, integration, and user acceptance testing.
Project | Data Privacy Violations | 4 | 3 | Ensure strict compliance with global data privacy regulations and conduct regular audits.
Project | Failure to Meet Aviation Industry Standards | 3 | 2 | Engage with industry regulators early and frequently validate compliance.
Project | Cost Overruns | 3 | 2 | Maintain a detailed budget with continuous cost monitoring and control.
Project | Poor User Experience | 3 | 2 | Perform user testing and incorporate feedback throughout development.
System | System downtime during Wi-Fi upgrade impacting customer experience | 3 | 4 | Schedule upgrades during off-peak hours, provide alternative connectivity options, and have a rollback plan.
System | Integration issues with IATA New Distribution Capability causing booking failures | 4 | 4 | Conduct thorough testing before implementation, ensure API compatibility, and maintain backup booking systems.
System | User adoption challenges for Delta Digital ID and personalization features | 2 | 2 | Conduct user training, collect feedback, and gradually roll out features to minimize resistance.
System | Increased latency or failure in personalized in-flight entertainment systems | 2 | 2 | Stress-test the system under different load conditions and implement caching strategies to improve performance.
Project | System complexity leading to extended project timelines and budget overruns | 4 | 4 | Follow Agile methodologies, maintain buffer time in planning, and have contingency budgets.
Project | Vendor or third-party API failures affecting booking, seat selection, or payments | 3 | 4 | Establish service level agreements (SLAs) with third-party vendors and monitor API performance continuously.
System | Inconsistent data synchronization between different travel segments (flight, hotel, car rentals) | 3 | 4 | Use real-time data synchronization tools and maintain redundant data backups to prevent inconsistencies.
Project | Negative customer feedback due to poor user experience with new features | 3 | 3 | Perform A/B testing, ensure seamless UI/UX design, and actively monitor customer complaints for rapid resolution.
System | Hardware Malfunction | 4 | 3 | Implement quality assurance testing and redundant hardware systems to prevent failures.
System | Outdated Firmware | 3 | 3 | Set up automated update mechanisms and perform regular security patches.
System | Non-Compliance with Data Retention Policies | 3 | 2 | Align with ICAO and FAA regulations, implement auto-archiving, and conduct regular compliance audits.
System | Malware Attacks | 4 | 4 | Employ intrusion detection systems, conduct regular penetration testing, and use secure firmware updates.
System | Incorrect Data Logging | 2 | 3 | Implement real-time validation algorithms and ensure synchronization with UTC timestamps.
Project | Environmental Damage | 3 | 3 | Design the black box with enhanced durability for extreme conditions and conduct climate stress testing.
System | Failure to Retrieve Data | 4 | 4 | Equip with real-time cloud backups.
System | Delayed Recovery | 3 | 3 | Increase data transmission frequency
Project | Service Disruptions (Department-Specific) | 3 | 2 | Clearly outline and document department-specific issues such as: flight delays (Operations), system downtime (IT), reservation failures (Customer Service). Assign responsibilities and establish escalation paths within each department to ensure timely resolution.
Project | Poor requirements quality | 4 | 4 | Conduct thorough stakeholder interviews, use clear documentation standards, and implement requirement validation sessions early in the project.
Project | Dependent delivery sequence | 3 | 3 | Use dependency mapping and critical path analysis to identify blockers early. Implement contingency planning and staggered sprints to reduce impact.
System | Configuration management | 3 | 3 | Use version control systems (e.g., Git), maintain configuration baselines, and conduct regular audits to prevent drift between environments.
System | Release management | 3 | 2 | Adopt CI/CD pipelines, automate testing, and use a release calendar with rollback plans for smoother deployment cycles.
System | Performance management | 4 | 3 | Establish performance benchmarks, use monitoring tools (e.g., New Relic), and conduct load testing throughout development.